## Team
Holiday
Weekend Off
Team Matrix | [6 empty] | Non Project Days
224
Sl No | Name | Email | Team | Hours | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Kunjal Lal | kunjallal.click@gmail.com | A1 | 56 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
2 | Aoushnik Aich | aichaoushnik@gmail.com | A1 | 56 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
3 | Shouvik Das | das2002shouvik@gmail.com | A1 | 56 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
4 | Sanchit Mathur | sanchitmat@gmail.com | A1 | 56 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8

## Backlog
Product Backlog | [5 empty] | 4
# | Feature ID | Module - (Nouns) | Feature - (Verbs) | Assigned To | Status | Effort in Hrs | Closure Date
1 | FE001 | Project Orientation | Project Walkthrough | A1 | DONE | 4 | 2024-07-27
2 | FE002 | Project Orientation | Understand Modules, Features and Data | A1 | DONE
3 | FE003 | Project Orientation | Document Requirements | A1 | DONE
4 | FE004 | Data Documentation | Create Data Dictionary | A1 | DONE
5 | FE005 | Data Documentation | Create Data Anomalies | A1 | DONE
6 | FE006 | Data Documentation | Create Data Generation Strategy | A1 | DONE
7 | FE007 | Data Preparation | Generate Data | A1 | DONE
8 | FE008 | Data Preparation | Inject and Identify Anamolies | A1 | DONE
9 | FE009 | Data Documentation | Prepare Data Statistics | A1 | IN-PROGRESS
10 | FE010 | DW Schema | Design DataStore | A1 | IN-PROGRESS
11 | FE011 | DW Schema | Create Database | A1 | OPEN
12 | FE012 | Data Preparation | Clean Data | A1 | OPEN
13 | FE013 | Data Migration | Migrate Data | A1 | OPEN
14 | FE014 | Data Transformation | Create Transformation Solution Design | A1 | OPEN
15 | FE015 | Data Transformation | Apply Transformation | A1 | OPEN
16 | FE016 | Data Transformation | Log Error Records | A1 | OPEN
17 | FE017 | Data Migration | Import into Database | A1 | OPEN
18 | FE018 | Data Analytics | Create Analytics Requirements | A1 | OPEN
19 | FE019 | Data Analytics | Generate Dashboards | A1 | OPEN
20 | FE020 | Data Analytics | Generate Reports | A1 | OPEN
21 | FE021 | Testing | Test the Worflows | A1 | OPEN
22 | FE022 | Testing | Identify Bugs | A1 | OPEN
23 | FE023 | Testing | Fix Bugs | A1 | OPEN
24 | FE024 | Project Closure | Prepare Presentation | A1 | OPEN
25 | FE025 | Project Closure | Prepare Project Docket | A1 | OPEN
26 | FE026 | Project Closure | Present to Project Stakeholders | A1 | OPEN

## Requirements Main
KPIs
Sl No | Title
1 | Increase Profit by 15% for next 2 Quarters
2 | 0% Error Rate in Accounting
3 | Increase takeaway profitablity by 10% for next 2 quarters
4 | Aquire 5 new clients over next 3 months
5 | Reduced Turn Around Time with Cashup and Banking
Workflows
Sl No | Title | Remarks
1 | Customer places order with a restaurant | All the data points and values related to the transactions that happen during this workflow to be captured and processed in the databaser and alteryx tool
2 | Delivery Partners deliver the order to the customer | Payment is made to the delivery partner, then delivery partner transfers the amount excluding the delivery charges to the restaurant back
3 | CashUp is published to the finance team | Cashup is publihsed to the finance team after reconciliation of sales, expenses and tax. Final amount isthen approved to be banked
4 | Cashup amount is banked by the designated employee | Once cashup is collected, same is remitted in the bank. Banking can happen across days either AM or PM. Exceptions are taken to bank despite not being reconciled
5 | Clients purchase subscription with ROS | Clients would like to purchase subscriptions with ROS and enable restaurants to be active on the ROS ERP. Each license is then assigned to the users of the portal. There are 2 products that are offerred by ROS -ROS ERP and ROS AI
Key Insights and Analytics
Sl No | Title | Remarks | Column1
1 | Increase Profit by 15% for next 2 Quarters | Delivery Profit, Dining Profit, delivery cost per restaurant, delivery paid to 3rd party service, delivery partner, Profit from date of activation | BEST TO WORST RESTAURANT
2 | 0% Error Rate in Accounting | Reconcile status is less for which restaurant (ADD CASHUP STATUS T0 IDENTIFY Difference), Formulae in backend, Internal Controls | RAG: Based on sales, revenue
3 | Increase takeaway profitablity by 10% for next 2 quarters | orders fulfilled, average order value(spent by customer per order),
4 | Aquire 5 new clients over next 3 months | Country w more profit, Which Category, Does it give Franchise,
5 | Reduced Turn Around Time with Cashup and Banking

## Rules
Sl No | Title | Priority
1 | Every Client, Restaurant and User should be uniquely identified in the system | P1
2 | One client can add many restaurants in the application | P1
3 | User package/subscription also should be captured. If the subscription has a limit of xx users, then user shouldn't be created. An error should be recorded | P1
4 | User Name and Unique ID cannot be changed during the migration process | P1
5 | Every user can belong to more than one restaurant. | P1
6 | User is inactivated when he/she resigns from the employment | P1
7 | Every subscription has per user license cost associated | P1
8 | User is assigned a role and department. One user would have one role and belong to one department | P1
9 | Each restaurant is configured with a specific currency - Depending on the primary transaction that would be applicable | P1
10 | When reports are displayed then amount should be calculated according to the user chose currency for reports. For example If am seeing the reports in INR then Pound has to be multiplied x times to get the INR value. Conversion according to the currency chosen | P1
11 | Countries are master data elements considering the restaurants available across countries. This gives flexibility to extend to other countries in the future | P1
12 | Orders are captured for each restaurant every day. | P1
13 | Orders information is captured according to the data defined in the sheet. An order can be either DineIn or HomeDelivery | P1
14 | Service Charges are applicable only for DineIn and Delivery Charges are applicable only for HomeDelivery orders | P1
15 | Order Total is food + drinks+other+charges(service or delivery). Tax is then calculated on this order total for final order total to be calculated | P1
16 | Tax information is available. Depends on the country. VAT if it is UK, GST if it is India. Data should capture information accordingly. If there’s a mismatch should be flagged for errors and reported back | P1
17 | Sales, Expenses, Delivery information is all captured end of day. This is then consolidated and reconciled as CashUp to be accounted and banked | P1
18 | Sales, Expenses, Delivery information are captured across orders for a given day for a given restaurant | P1
19 | Every Cash-up is for a specific restaurant. Each day Cash-up is generated at the end of day. This captures information about sales and expenses for the day with remaining balance end of day | P1
20 | If an order has HomeDelivery as the type, those orders would have delivery charges which are delivered by partners UberEATS and Justeats | P1
21 | End of the day they send the information across all the orders total amount collected from the user and transfer via API | P1
22 | Order Amount should be equal to API amount if not there is a mismatch and should be reconciled. Again this is for a given restaurant and sent end of day by the delivery partner | P1
23 | Sales captured in cashup should be excluding tax as it is captured in a separate column | P1
24 | Service charges is considered as 5% on the order value | P1
25 | Partner is paid 6% on every order that is delivered. 10% is delivery charges however, 6% is to the partner and 4% to the restaurant | P1
26 | End of day when the partner is sending the delivery amount, they will deduct the 6% and send the final amount. This has to be reconciled in our accounting system. So essentially, 4% of delivery of total delivery charges is our revenue | P1
27 | EOD amount should be reconciled and match. BOD + Sales - Expenses-partner_delivery_charges should be equal to the EOD amount entered by the user. If not matching has to be flagged | P1
28 | If there is no mismatch, then admin publishes the cashup and all the published cashups are deposited in the bank | P1
29 | Deposit into bank can happen every day or after 2-3 days interval. Data should be reconciled accordingly | P1
30 | Exception cases admin can decide to proceed with banking | P1
31 | The same structure of data will be available everyday to migrate and transform. Repeatable cycle for migration and transformation should be established | P2
32 | Master Data should be available in our database and checked every time excel is migrated. If a new master data like country, currency is found then has to be added into the master data table | P2

## Data Cleaning Matrix
Transformation Tracker
|  |  | 1286510 | 121
Sl No | Data Set | Data Generated | Rows | Columns | Cleaning Status | Null Value | Multiple Lines | Date Format | Number Format | Spellings | Casing | Formula | Condition
1 | Clients | YES | 30 | 6 | YES | YES | YES | YES | YES | YES | YES | YES | YES
2 | Restaurants | YES | 98 | 13 | YES | YES | YES | YES | YES | YES | YES | YES | YES
3 | Roles | YES | 4 | 5 | YES | YES | YES | YES | YES | YES | YES | YES | YES
4 | Departments | YES | 9 | 3 | YES | YES | YES | YES | YES | YES | YES | YES | YES
5 | Users | YES | 448 | 13 | YES | YES | YES | YES | YES | YES | YES | YES | YES
6 | Subscriptions | YES | 8 | 10 | YES | YES | YES | YES | YES | YES | YES | YES | YES
7 | Countries | YES | 250 | 5 | YES | YES | YES | YES | YES | YES | YES | YES | YES
8 | Currencies | YES | 4 | 3 | YES | YES | YES | YES | YES | YES | YES | YES | YES
9 | Orders | YES | 806520 | 13 | YES | YES | YES | YES | YES | YES | YES | YES | YES
10 | Sales | YES | 71535 | 10 | YES | YES | YES | YES | YES | YES | YES | YES | YES
11 | Deliveries | YES | 221451 | 7 | YES | YES | YES | YES | YES | YES | YES | YES | YES
12 | CashUps | YES | 71535 | 12 | YES | YES | YES | YES | YES | YES | YES | YES | YES
13 | TaxInfo | YES | 2 | 4 | YES | YES | YES | YES | YES | YES | YES | YES | YES
14 | Expenses | YES | 71535 | 9 | YES | YES | YES | YES | YES | YES | YES | YES | YES
15 | Bankings | YES | 43081 | 8 | YES | YES | YES | YES | YES | YES | YES | YES | YES

## Transformation Matrix
Transformation Tracker
|  |  | 1286510 | 121
Sl No | Data Set | Data Generated | Rows | Columns | Transformation Status | Data Cleansing | Cross Tab | SelectAll | Formula | Sort Tool | Unique Tool | Filter | Join | Replace | Input | Output | Browse | Sample | MultiField | Summarise | Transpose | Arrange | Auto Fill | Dynamic Input | Record ID | Macros | Random Sample
1 | Clients | YES | 30 | 6 | NO | YES
2 | Restaurants | YES | 98 | 13 | NO | YES
3 | Roles | YES | 4 | 5 | NO | NO
4 | Departments | YES | 9 | 3 | NO | NO
5 | Users | YES | 448 | 13 | NO | YES
6 | Subscriptions | YES | 8 | 10 | NO | NO
7 | Countries | YES | 250 | 5 | NO | NO
8 | Currencies | YES | 4 | 3 | NO | NO
9 | Orders | YES | 806520 | 13 | NO | YES
10 | Sales | YES | 71535 | 10 | NO | YES
11 | Deliveries | YES | 221451 | 7 | NO | YES
12 | CashUps | YES | 71535 | 12 | NO | YES
13 | TaxInfo | YES | 2 | 4 | NO | YES
14 | Expenses | YES | 71535 | 9 | NO | YES
15 | Bankings | YES | 43081 | 8 | NO | YES

## Data Generation Strategy
Sl No | Sheet | Title
1 | Client | Market Research (Understand market size of casual, fast, ethnic, fine dining): 40%, 25%, 20%, 15% respectively
2 | Restaurants | Client to restaurant ration, Checked whether client provides Franchise or not
3 | User | if big restaurant more users, subscription on basis of size
4 | Orders | Delivery% remaining is dine in Fast Casuals >= 50%, casual <=30%, ethnic<=20%, fine dining < 10%
5 | Sales to Expenses | ranges from 2:1 to 3:1
6 | Sales | Derived from orders, group by retaurant ID and date
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31

## Deliverables and Focus
Sl No | Deliverable | From | Priority
1 | Project Synopsis Document | TGL | P1
2 | Requirements Docket | TGL | P1
3 | Data Dictionary | Team | P1
4 | DW Schema | Team | P1
5 | Solution Design Docket | Team | P1
6 | Unclean DataSet | Team | P1
7 | Clean DataSet | Team | P1
8 | Data Cleaning Docket | Team | P1
9 | Data Transformations Docket | Team | P1
10 | Test Cases | Team | P1
11 | Dashoards and Reports | Team | P1
12 | Project Presentation to Managers | Team | P1

## Release Calendar
Release Calendar
|  | M | T | W | T | F | S | S | M | T | W
Sl No | Name | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Project Walkthrough | bar: T
2 | Requirements Gathering | bar: T
3 | Clarification Log and Discussion | bar: T
4 | Data Set Preparation | bar: T to T
5 | Data Dictionary | bar: T
6 | Requirement Documentation | bar: T
7 | Solution Design | bar: F
8 | Data Transformation | bar: F to S
9 | Data Migration into Mart | bar: S
10 | Dashbaords and Reports | bar: S
11 | Testing | bar: S to S
12 | Release 1 | bar: S
13 | Release 2 | bar: S
14 | Final Release | bar: M
15 | Presentation - TGL, College, CEO | bar: M
16 | Mock Interviews/Presentations | bar: T
17 | Final Project Presentation | bar: W

## Sheet1
DW | Postgres | ER